## Slide 1
Chart: 
| Open | Closed in 1 Day | Closed in 1 Wk | Closed > 1 Wk
High | 0 | 0 | 0 | 0
Medium | 0 | 0 | 0 | 0
Low | 0 | 0 | 0 | 0
PROJECT FLASH REPORT
Project: Identity Proofing Soltuion
Client Executive: V.Jay LaRosa
OpenSky Manager: John Clay
OpenSky Consultant(s): Faith Vicinanza / PM; Michael Zygma / SA; Gautham Ravi / BA;
Period Ending: 05-20-2106
ISSUES MANAGEMENT ACTIVITY
F. Work plan Status Update:
GENERAL STATUS:
GREEN
Chart: 
| Project Startup | Pgm Sprint 1: Pilot the Helpdesk | Pgm Sprint 2: PoC Exec/Assess; Scale Helpdesk | Pgm Sprint 3: Draft Processes | Dev Sprint 1: PoC API (online reg) | Pgm Sprint 4: Tune Service | Dev Sprint 2: Iteratively Dev/Test API | Pgm Sprint 5: Design metrics | Dev Sprint 2: Sec non-functional ctrls/hardening | Pgm Sprint 6: Refine processes & tune svc | Dev Sprint 3: Respond to tuning changes | Program Sprint 7: Document controls & establish metrics monitoring
% Complete | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% Remaining | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
E. Budget to Actual: Total Est. Project Hours 5931
Client Confidential
A. Key Activities and Occurrences This Period
OpenSky team members onboarded (PM and 2 Sec Arch.s)
Identified initial requirements and limitations for tactical portal and federated access, as well as long term service based API calls for registration use.
Gained insight to ADP security standards related to project.
Drafted Project Plan, vetted and tracked Spint 1 activities, place holders established for Sprint 2 activities.
Drove Questions and Configuration Settings for the ADP/IDology Identity Proofing Portal to enable CSRs on 5/20.
Provided support for Development Team responsible for building Identity Proofing calls to the IDology service APIs.
Assisted in resolving interface and coding questions between ADP and IDology.
Engaging with Development Team on design. Began 5/19.
Scheduled training of CSRs.
B. Key Activities and Occurrences for Next Period
Complete draft Project Plan – baseline it with ADP.
Assist ADP with onboarding and training remaining CSR population.
Engage more with Architecture and Development contacts to fully understand methodology used in project delivery to enhance security components.
Provide recommendations and support for a successful implementation and operation of ADP’s Identity Proofing components within IDM.
Manage status calls and ensure robust communications across all teams.
C. Planned Work Products:
Business Design and Technical Design documentation (ADP w/ support from OpenSky)
Baselined project plan
Status reports, meeting minutes.
D. Key Issues:
Project velocity requires diligence and strong participation from all stakeholders.
Chart: 
Hours Incurred | 284.5
Estimated Hours Remaining | 5646.5
Note: Based on est. project hours, OpenSky has realized a 5% completion rate.