## ADP Executive Summary Proj Plan
ADP Identity Proofing Solution - Executive Summary Project Plan - as of 6/23 (pending new release dates from Dev group)
Sprint or Workstream | Status | w/e 5/13 | w/e 5/20 | w/e 5/27 | w/e 6/3 | w/e 6/10 | w/e 6/17 | w/e 6/24 | w/e 7/1 | w/e 7/8 | w/e 7/15 | w/e 7/22 | w/e 7/29 | w/e 8/5 | w/e 8/12 | w/e 8/19 | w/e 8/26 | w/e 9/2 | w/e 9/9
Sprint 1: Vendor Selection / PoC/re-enable Help Desk | Comp.
Sprint 2.a: Scale up the help desk (IDology) | Comp.
Sprint 2.b: Business Operations: Fraud Management | Comp.
Sprint 2.c: Online Registration Design | I/P
Sprint 3: Draft processes | I/P
Workstream 1.a: Reassess vendor | Comp.
Workstream 2.b: Convert design/workflows/etc. to LN | I/P | [8 empty] | at risk
Workstream 2.b: Migrate CSR registration path to LexisNexis | I/P
Development Sprint 1: PoC API for online registration | I/P
Sprint 4 / Tune service and design metrics | NS | [5 empty] | Not Started
Development Sprint 2: Iteratively Dev/Test API & Hardening | I/P
Sprint 5: Refine processes & tune service - Iterative | NS
Sprint 6: Document controls & Establish Metrics Monitoring | NS
Go Live | NS
Post Go-Live | NS
Workstream 3.a: Threat Model v1.0 - for first release | Comp.
Workstream 3.b: Threat Model v3.0 - long view assessment | I/P
Workstream 4: Adding Security Controls (noCAPTCHA) | I/P
Workstream 5: RUN integration | I/P
Workstream 6: BU call center assessment / recommendation | I/P
Workstream 7: ADP home grown KBA capabilities - design | NS
Workstream 8: Call center roll out | TBD
Workstream 9: ADP KBA capabilities - build / deploy / train | TBD
Parking Lot #1: AD Group | TBD
Parking Lot #2: Sitewide automation detection - reconsider F5 | TBD
Parking Lot #3 User Attribute or similar identity health tracking solution - OpenSky proposal is in progress | TBD